## Roadmap
Item | Track | Status | Target | Owner | Notes
Central hub (dashboards + roadmap + docs) | Ops & Tooling | In Progress | Jul 2026 | Shivank | This site — gsheet-driven roadmap
fse_v1 first-session engagement experiment | Web App | In Progress | Jul 2026 | Shivank | A/B/C live; readout when sample sufficient
Play Store production app (com.wiomtv.android.prod path) | Android App | In Progress | Aug 2026 | Shivank | Signing key reset pending account owner
Pilot household rollout (v1.0-pilot) | Android App | In Progress | Jul 2026 | Shivank | On Mi TV; founder visual checks open
Channel lineup expansion (54 staged) | Content | In Progress | Aug 2026 | Shivank | iptv-org pipeline; ffprobe-validated HLS
Wiom TV entry on payment-success page | Growth | Planned | Aug 2026 | Shivank | Awareness-first banner; final design pending
Customer-app entry on unserviceable screens | Growth | Planned | Aug 2026 | Shivank | Prototype live; needs org repo write access
Microdrama ₹10 paywall entry | Growth | Planned | Sep 2026 | Shivank | Mockups ready in microdrama_mock
TV installer (Remote v2, no-human APK) | Android App | On Hold | TBD | Shivank | Protocol unproven vs real TV

## Documents
Title | Type | Link | Owner | Notes
Production plan (path to Play Store) | Plan |  | Shivank | Add link — lives at ~/wiom-tv-android/PRODUCTION_PLAN.md
Zero-based app decision framework | Framework |  | Shivank | Add link — zero_based_app/00_decision_framework.md
Phase 0 inherited-work summary (Jira WT) | Research |  | Shivank | Add link — inherited_summary.md